# AcreForge: Family Business Launch Guide

Prepared: October 28, 2026

For: The founder and his mom

Working product name: AcreForge (accepted by the founder; not yet cleared for legal or trademark use)

Purpose: Give Mom a practical secretary/coordinator role while the founder decides how to protect, form, and launch the product.

This is an organizing guide, not legal, tax, or financial advice. Verify current requirements with Oregon and federal agencies and consult an Oregon small-business attorney and tax professional before filing, assigning ownership, or taking payments.

# What AcreForge is today

AcreForge is a working browser-based prototype for early planning of rural land, estates, homes, and buildings. Its code and project files are in the AcreForge folder. The current README says account sign-in, cloud saving, paid plans, and payment processing are not active. Project data is saved in the browser, and the map/site outputs are conceptual planning references—not surveys, engineering, zoning, permits, or legal property data.

That means the first business goal is protect and organize the work, validate the name and customer need, and make a deliberate ownership decision—not to turn on payments immediately.

# Recommended division of responsibilities

| Person | Suggested role | Responsibilities |
| --- | --- | --- |
| Founder | Product owner and decision-maker | Decide product direction, approve name/ownership/expenses, keep building the app, and approve anything published or legally filed in his name. |
| Mom | Secretary / launch coordinator | Maintain the checklist and deadlines, organize receipts and project records, gather quotes, book professional consultations, track name/domain searches, and prepare forms for the founder to review. |

Mom's help does not automatically make her an owner, officer, employee, or authorized signer. If she will own part of the company, contribute money in exchange for ownership, or have authority to sign or access accounts, discuss and document that explicitly with an attorney and tax professional. Do not share passwords; use appropriate account permissions and a password manager.

If the founder is under 18: pause before filing, signing contracts, opening financial accounts, or accepting payments. Ask an Oregon attorney and the bank/payment provider what an adult must do and how to preserve the founder's intended ownership. Do not put an adult's name on the business as owner just to get through a form without first agreeing on the legal and tax consequences.

# Name shortlist

Keep AcreForge as the product/brand name for now. A legal company name can be different from the product name. These are ideas only; none has been checked for Oregon availability, trademarks, domains, or confusingly similar businesses.

| Rank | Possible legal entity name | Notes |
| --- | --- | --- |
| 1 | AcreForge Software LLC | Clear, broad enough for the current web product; best starting candidate if available. |
| 2 | AcreForge Technologies LLC | Broader if the company later offers more than one software product. |
| 3 | AcreForge Land Tools LLC | Descriptive and product-focused. |
| 4 | AcreForge Planning Systems LLC | Emphasizes planning software, but is longer. |
| 5 | AcreForge Digital LLC | Flexible, but less specific. |
| 6 | AcreForge Studio LLC | Friendly and broad, though less obviously software. |
| 7 | AcreForge Labs LLC | Suggests product development; may sound experimental. |
| 8 | AcreForge Holdings LLC | Usually not the clearest choice for the operating company; discuss with counsel/accountant before considering. |

Recommendation: check AcreForge Software LLC first, while continuing to use AcreForge as the product name. Do not print “LLC,” claim a registered trademark, buy a costly domain, file an entity, or announce the name as cleared until the availability checks and ownership decision are complete. Oregon approval of a legal entity name is not the same as federal trademark clearance.

# Mom's secretary checklist

## Phase 1 — Organize and decide before filing

[ ]  Create a private business folder for official records; keep it separate from public website files.

[ ]  Record who created or contributed code, text, artwork, designs, and documentation; keep dated source backups and copies of relevant project history.

[ ]  Make a one-page asset inventory: repository/site, domain and hosting accounts, PDFs/manuals, logos, third-party libraries/data, and any payment or fundraising code.

[ ]  Confirm who should own the product and any future company. Write down any proposed founder/mom ownership split, cash contributions, repayment expectations, and work contributions for professional review.

[ ]  Book a short consultation with an Oregon small-business attorney and a tax preparer/CPA. Ask about age/capacity if applicable, ownership and IP assignment, LLC versus sole proprietorship, taxes, and insurance.

[ ]  Prepare a simple customer-interview list: rural landowners, farm/estate planners, builders, or other likely users. Record the problem, current workaround, must-have features, and willingness to pay. Do not promise features or delivery dates.

## Phase 2 — Clear the name and protect the work

[ ]  Search Oregon's Business Registry for exact and similar entity names.

[ ]  Search the USPTO Trademark Search system for “AcreForge” and similar spellings/sounds in relevant software and planning-service categories. Search the wider web, app stores, domains, and social handles too.

[ ]  Ask a trademark attorney to assess confusingly similar marks before investing in branding or filing. A domain or Oregon company-name approval does not grant trademark rights.

[ ]  Decide whether to form an entity only after the founder understands fees, reporting, taxes, liability, and ownership obligations. Confirm current Oregon filing and annual-report fees directly with the Secretary of State.

[ ]  Keep source-code history, dated releases, and contributor records. Copyright generally protects original expression (such as code and written material), not an idea, feature concept, or brand name. Ask counsel whether and when to register copyright in the software and documentation.

[ ]  If an entity is formed, have counsel prepare/review an operating agreement and written IP assignment/license so ownership of existing work and future contributions is clear. Do not assume incorporation automatically transfers the founder's existing code to the company.

[ ]  Use TM only as an unregistered brand claim if appropriate; use ® only after federal registration and only for the registered goods/services.

## Phase 3 — Set up basic business administration

[ ]  If forming an LLC/corporation, register with Oregon first; then apply for an EIN directly from the IRS if required or useful. The IRS EIN application is free—avoid paid third-party EIN sites.

[ ]  Set up a business bank account only after the entity/ownership and bank requirements are settled. Keep business and personal money separate; save invoices and receipts.

[ ]  Set up bookkeeping with categories for hosting/software, legal/accounting, development, marketing, and customer refunds/support. Record who paid each expense and whether it is a loan, contribution, or reimbursement.

[ ]  Check city/county business-license requirements and Oregon/federal tax obligations for the actual location and business model.

[ ]  Decide who receives official mail and tracks deadlines. Calendar Oregon annual reports, tax filings, domain renewal, hosting renewal, and insurance reviews; never let a filing notice go unanswered.

[ ]  Ask an insurance broker whether general liability, professional liability/errors and omissions, cyber, or other coverage is appropriate before public launch.

## Phase 4 — Make the product ready before selling

[ ]  Keep the current prototype and all accounts backed up; test restore from a backup.

[ ]  Finish and test the core user journeys on desktop and mobile, including importing/exporting projects, browser storage behavior, accessibility, and error states.

[ ]  Write plain-language product limits: conceptual planning only; not a survey, legal boundary, permit/zoning determination, engineering design, or professional advice.

[ ]  Review privacy/data practices and decide what information is collected, where it is stored, retention/deletion, support contact, and incident response. Publish a privacy notice and terms reviewed for the intended markets.

[ ]  Before accounts/cloud saving: choose a secure architecture, access controls, account recovery, deletion/export, backups, and security testing. Do not place secret keys or authorization logic in browser JavaScript.

[ ]  Before payments: build and test server-side checkout and entitlements, receipts, refunds/cancellations, taxes as applicable, support, and honest pricing. The current README says payments are not active and that the existing Stripe webhook is not a complete billing system.

[ ]  Verify rights and license obligations for bundled libraries, map/geospatial sources, fonts, imagery, and other content. Preserve required notices and attribution.

[ ]  Run a small private beta with consent; record bugs and user feedback. Do not advertise accuracy or capabilities beyond what has been tested.

[ ]  Agree on support ownership, response time, launch budget, refund approach, and what happens if the service is paused or discontinued.

## Phase 5 — Launch decision

[ ]  Review entity, trademark, copyright/IP, tax, privacy, terms, security, product limitations, insurance, and support with the appropriate professionals.

[ ]  Confirm the company owns or has permission to use every asset it needs.

[ ]  Confirm the live site has no test secrets, test payments, unfinished fundraising claims, or misleading promises.

[ ]  Approve a written launch checklist and a rollback plan. Make a separate go/no-go decision before accepting any customer money.

# Suggested first meeting (30 minutes)

1. Founder: describe the product, intended customers, current state, and what help is wanted.

2. Together: decide whether Mom is only a coordinator or may be a co-owner/paid worker; do not leave this implied.

3. Mom: start the asset inventory and create a deadline/contact sheet—without collecting passwords or private tax/identity documents.

4. Together: select one business-name candidate to investigate, not to assume is available.

5. Mom: book an attorney/CPA consultation and prepare the questions above.

6. Founder: continue product work and customer interviews; do not accept payments until the launch gates are met.

# Questions to take to professionals

Attorney: Who owns the existing app and brand? What entity and ownership arrangement fits the founder's age and plans? How should Mom's role be documented? What IP assignment, contributor agreement, terms, privacy, and liability language is needed? Is the name clear enough to use and protect?

Tax professional: What federal/Oregon tax registrations and filings apply? How should startup expenses and money from family be recorded? What changes if the founder is a minor, Mom is paid, or Mom owns a share? What sales taxes or other transaction taxes could apply to the intended customers and products?

Bank/payment provider: What formation and identity documents are required? Who can be an account owner/signatory? What age limits, reserves, refund procedures, and prohibited-business rules apply?

# Official starting points

•  Oregon Secretary of State, Business Registry: https://sos.oregon.gov/business/Pages/register.aspx

•  Oregon Secretary of State filing portal: https://secure.sos.state.or.us/cbrmanager/

•  U.S. Small Business Administration, choose a business structure: https://www.sba.gov/business-guide/launch-your-business/choose-business-structure

•  IRS, Employer Identification Numbers (EIN): https://www.irs.gov/businesses/employer-identification-number

•  USPTO, trademark search: https://www.uspto.gov/trademarks/search

•  USPTO, what a trademark is: https://www.uspto.gov/trademarks/basics/what-trademark

•  U.S. Copyright Office registration portal: https://www.copyright.gov/registration/

•  U.S. Copyright Office, computer programs and other digital content: https://www.copyright.gov/registration/other-digital-content/

Check all fees, rules, and URLs directly with the agencies at the time of filing; they can change.